## Daily Production Report Templat
DAILY PRODUCTION REPORT
Production info
Field | Value
Production | SALT FLATS
Company | Dry Creek Pictures LLC
Shoot day | Day 4 of 12 (8 remaining)
Date | Thursday, October 8, 2026
Sets | Hardesty Salvage (office, yard); Tumbleweed Diner
Director | Lena Okafor
Line producer / UPM | Rosa Delgado
1st AD | Kyle Brandt
Prepared by | Mina Park, 2nd AD
Status | On schedule
Weather | Sunny, high 83 F
Times
Event | Time
Crew call | 7:00 AM
Shooting call | 8:00 AM
First shot | 8:14 AM
Lunch | 12:45 PM to 1:15 PM
Company move | Left Hardesty Salvage 1:20 PM, arrived Tumbleweed Diner 1:55 PM
First shot after lunch | 2:50 PM
Camera wrap | 6:52 PM
Last person out | 8:05 PM
Scenes, pages, and setups
| Scenes | Pages | Setups
Script total | 44 | 70
Scheduled to date | 16 | 24 7/8
Shot previously | 12 | 18 | 58
Shot today | 4 | 6 7/8 | 20
Total to date | 16 | 24 7/8 | 78
Remaining | 28 | 45 1/8
Scenes shot today
Sc. | Set | Pages | Setups | Status
13 | INT. HARDESTY SALVAGE - OFFICE | 2 5/8 | 7 | Complete
12 | EXT. HARDESTY SALVAGE - YARD | 1 3/8 | 4 | Complete
17 | INT. TUMBLEWEED DINER | 1 | 4 | Complete. Insert 17E (badge) owed, added to Day 9.
16 | INT. TUMBLEWEED DINER | 1 7/8 | 5 | Complete
Cast times (must match signed Exhibit G)
# | Character | Performer | Status | Report MU/WD | Report on set | 1st meal start | 1st meal finish | Dismiss on set | Dismiss MU/WD | MPVs | Ex. G signed
1 | DELL | Marco Ybarra | W | 7:20 AM | 7:55 AM | 12:45 PM | 1:15 PM | 6:55 PM | 7:10 PM | 0 | Yes
2 | JUNE | Tessa Quill | W | 6:50 AM | 7:55 AM | 12:45 PM | 1:15 PM | 6:55 PM | 7:10 PM | 0 | Yes
3 | HOLLIS | Glenn Hardesty | W | 7:00 AM | 7:55 AM | None | None | 12:35 PM | 12:50 PM | 0 | Yes
5 | DEPUTY PACE | Curtis Vail | SW | 12:30 PM | 2:30 PM | None | None | 5:15 PM | 5:30 PM | 0 | Yes
8 | BEV | Donna Kell | SWF | 1:15 PM | 2:30 PM | None | None | 6:35 PM | 6:45 PM | 0 | Yes
Background and stand-ins
Qty | Type | In | Out | Vouchers
6 | Diner patrons (Sc. 16, 17) | 1:00 PM | 6:40 PM | 6 of 6 collected
2 | Stand-ins (Dell, June) | 7:30 AM | 6:55 PM | 2 of 2 collected
Media
Item | Today | To date
Camera cards (A-cam) | A019 to A024 (6 cards) | 24 cards
Data offloaded, verified | 1.4 TB | 5.3 TB
Sound files | 112 | 431
Crew times
Dept | Position | Name | In | Out
Production | 1st AD | Kyle Brandt | 6:30 AM | 7:30 PM
Production | 2nd AD | Mina Park | 6:15 AM | 7:55 PM
Camera | 1st AC | Carla Reyes | 6:30 AM | 7:40 PM
Locations | Location manager | Walt Kemper | 6:00 AM | 8:05 PM
Delays, incidents, and notes
Time | Note
8:00 AM | Crusher ran until 8:14 AM despite agreed 8:00 AM shutoff. First shot delayed 14 min. Locations spoke with owner.
1:20 PM | Company move took 35 min, arrived 1:55 PM.
5:15 PM | Pace released after 17D as planned. Badge insert 17E not shot. Added to Day 9 at warehouse set.
Equipment: 50mm prime flagged for back focus by 1st AC. Returned to rental house, replacement due Day 5.
Injuries: none. Property damage: none.
Template by Storiara (storiara.com). Free to use and modify.